## Sheet1
			Requirement				Development					SAT		Closing
			October				November					December					Jan
	Weight	Status	W1	W2	W3	W4	W5	W6	W7	W8	W9	W10	W11	W12	W13	W14	W15
Kick Off	1	1
Collaboration Tools
Slack	2	1
Github	2	1
Team Setup	2	1
Ideas
Brainstorming	1	1
Decision	3	1
Resources
Database
Dataset	3
Database Setup	3
Architecture	2	1
Server Configuration	3	1

Documentation
Project Timeline	1	1
Team Structure	1	1
Process Flow	1
Mock-up	1
Architecture	1	1
Modules
POC	3
Geographical Info
Visualisation	5
Data Processing	3
Logic	4
Historical weather data
Visualisation	5
Data Processing	3
Logic	4
Interactive Simulation
Visualisation	4
Data Processing	3
Logic	5
Testing
System Acceptance	5

Progress	27%
				Planned
				On Schedule
				On Progress
				Late, Need to speed up

Marios		Database Setup
Salingga		Documentation & Websocket
Jun		Find out jquery/angular.js & create 1 chart page w/ dummy data
Kan		Find out d3.js & create 1 chart page w/ dummy data
Ronald		create data collection -> send to client (ajax/json)
Kelvin		find out about API/scrapping
Christina		find dataset for weather

		Deadline: Wed, 9th Nov 10:00